## Sheet1
Cavallino data consolidate from Old POS to Portal(Reports)
| Activities | Estimated date to finish | Status
From old POS
- End of Day
- Generate Access DB | Access Database
Totals.accdb
Master.accdb
To portal MYSQL Database
- Get data from accdb File to Mysql Database | Tables
| menuitemsales | December 08, 2019 | Done
| financial | December 08, 2019 | Done
| order | December 08, 2019 | Done
| invoice | December 08, 2019 | Done
| payment | December 14, 2019 | Done
| tender | December 14, 2019 | Done
PORTAL
- Generate consolidated Reports
| Hourly PMIX Report | December 15, 2019 | Done
| Daily PMIX Report | December 15, 2019 | Done
| Financial Report | December 15, 2019 | Done
| Certificate Summary Report | December 16, 2019 | Done
| Charge Summary Report | December 16, 2019 | Done
| Check Summary Report | December 16, 2019 | Done
| Credit Summary Report | December 16, 2019 | Done
| Debit Summary Report | December 16, 2019 | Done
| Discount Summary Report | December 16, 2019 | Done
| Sales Summary Report | December 16, 2019 | Done
| Tender Summary Report | December 16, 2019 | Done
| Tax and Service Charge Summary Report | December 17, 2019 | Pending
| Tender Total Summary | December 17, 2019 | Pending
| Employee Closed Checks | December 18, 2019 | Pending
| Cancelled, Refund and Void Report | December 18, 2019 | Pending